## Employee_Master
employee_id | employee_name | department | role_name | daily_capacity_hours | skill_group | active_flag
EMP-001 | 山田 太郎 | Construction | Site Lead | 8 | Security | Y
EMP-002 | 佐藤 花子 | Construction | Technician | 8 | Security | Y
EMP-003 | 鈴木 一郎 | Engineering | Planner | 8 | Planning | Y

## Project_Master
project_id | project_name | customer_name | project_manager_id | start_date | end_date | status | priority | planned_total_hours
PRJ-001 | 本社入退室更新 | Alpha Facilities | EMP-001 | 2026-09-01 | 2026-09-30 | DRAFT | High | 120
PRJ-002 | 支店監視カメラ更改 | Beta Office | EMP-002 | 2026-09-05 | 2026-10-10 | APPROVED | Medium | 160
PRJ-003 | 倉庫制御盤点検 | Gamma Logistics | EMP-003 | 2026-09-08 | 2026-09-18 | ISSUED | Low | 48

## Project_Schedule
schedule_id | project_id | task_name | responsible_employee_id | schedule_date | planned_hours | schedule_status | progress_percent
SCH-001 | PRJ-001 | 現地調査 | EMP-001 | 2026-09-10 | 4 | Planned | 20
SCH-002 | PRJ-001 | 機器設定 | EMP-002 | 2026-09-10 | 6 | Planned | 35
SCH-003 | PRJ-002 | 配線工事 | EMP-001 | 2026-09-11 | 5 | Planned | 50
SCH-004 | PRJ-002 | 試験調整 | EMP-002 | 2026-09-11 | 4 | Planned | 50
SCH-005 | PRJ-003 | 定期点検 | EMP-003 | 2026-09-12 | 7 | Planned | 60

## Resource_Input
entry_id | employee_id | work_date | project_id | task_name | planned_hours | availability_status | remarks | source_file | last_refresh_at
EMP-001-2026-09-10-01 | EMP-001 | 2026-09-10 | PRJ-001 | 現地調査 | 4 | Assigned | 午前対応 | EMP-001.xlsx | 2026-09-09 09:00
EMP-001-2026-09-10-02 | EMP-001 | 2026-09-10 | PRJ-002 | 資材手配 | 5 | Assigned | 午後対応 | EMP-001.xlsx | 2026-09-09 09:00
EMP-002-2026-09-10-01 | EMP-002 | 2026-09-10 | PRJ-001 | 機器設定 | 6 | Assigned |  | EMP-002.xlsx | 2026-09-09 09:00
EMP-002-2026-09-11-01 | EMP-002 | 2026-09-11 | PRJ-002 | 試験調整 | 4 | Assigned |  | EMP-002.xlsx | 2026-09-09 09:00
EMP-003-2026-09-12-01 | EMP-003 | 2026-09-12 | PRJ-003 | 定期点検 | 7 | Assigned |  | EMP-003.xlsx | 2026-09-09 09:00

## Progress_Input
progress_entry_id | employee_id | project_id | progress_date | progress_percent | actual_hours | progress_status | issue_flag | update_comment | source_file | last_refresh_at
PRG-001 | EMP-001 | PRJ-001 | 2026-09-10 | 35 | 3.5 | In Progress | N | 現地調査完了 | EMP-001.xlsx | 2026-09-09 09:00
PRG-002 | EMP-002 | PRJ-002 | 2026-09-11 | 50 | 4 | In Progress | Y | 部材待ち | EMP-002.xlsx | 2026-09-09 09:00
PRG-003 | EMP-003 | PRJ-003 | 2026-09-12 | 60 | 7 | Done | N | 点検完了 | EMP-003.xlsx | 2026-09-09 09:00

## General_Resource
resource_row_id | employee_id | employee_name | department | work_date | project_id | project_name | task_name | planned_hours | daily_capacity_hours | total_daily_hours | utilization_rate | overload_flag | available_hours | progress_percent | progress_status | issue_flag

## Dashboard
CConstructionAI Resource Dashboard
Base Date | 2026-09-10 |  |  | Refresh
Import RefreshAll.bas into an .xlsm copy and assign Refresh_All_Resource_Management to a button.
Metric | Value | Status Guide |  |  | Project Status | Count
Total Employees |  | OVER | 過負荷 |  | Issue
Active Projects |  | Y | 課題あり |  | Normal
Assigned Hours (Base Date)
Average Utilization
Overloaded Rows
Available Hours
Issue Projects